## GENERAL
|  |  | GENERAL | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
GENERAL/PROJECT MANAGEMENT
| PROJECT SCHEDULE |  |  | X | X
| SHEET INDEX |  |  | X | X
ADDRESSING PLAN
|  | SUBMITT | [5 empty] | X | X
|  | APPROVAL | [7 empty] | X | X
| SCHEDULE ORB TEAM MEETINGS |  |  | X | X
| BUILDING KEY PLAN |  |  |  |  | X | X
| DESIGN CHECKLIST |  |  |  |  | X | X

## A1.xx LS COVER
|  |  | A1.xx LIFE SAFETY COVER | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
LIFE SAFETY COVER INFORMATION
LIFE SAFETY KEY PLAN
|  | KEY PLAN | [5 empty] | X | X
|  | BLDG NUMBER | [5 empty] | X | X
|  | SECTION TAG | [5 empty] | X | X
|  | FIRE WALL LABELS | [5 empty] | X | X
|  | ORB TITLE & NORTH ARROW | [5 empty] | X | X
LIFE SAFETY KEY SECTION
|  | SECTION | [5 empty] | X | X
|  | COLOR CODE OF FIRE ASSEMBLIES (WALLS, FLOOR-CEILING AND ROOF-CEILING) | [5 empty] | X | X
|  | BLDG NUMBER AND OCCUPANCY TYPE | [5 empty] | X | X
|  | BUILDING LEVELS AND GRADE LEVEL | [5 empty] | X | X
|  | CONSTRUCTION TYPE | [5 empty] | X | X
|  | EXIT DISCHARGE LEVEL | [5 empty] | X | X
|  | CALLOUT OCCUPANCY SEPARATION (SEPARATED USE, NON-SEPARATED USE, ACCESSORY USE, ETC) | [5 empty] | X | X
|  | FIRE WALL LABELS | [5 empty] | X | X
| FLAME SPREAD AND FINISHES FIRE CLASSIFICATION (IBC 803.11) | [6 empty] | X | X
| ACCESIBILITY COMPLIANCE | [6 empty] | X | X
| OCCUPANT LOAD ANALYSIS PER BUILDING | [6 empty] | X | X
| OCCUPANT LOAD ANALYSIS PER COURTYARD AREA | [6 empty] | X | X
| BUILDING AREA ANALYSIS | [6 empty] | X | X
| BUILDING CODES LIST | [6 empty] | X | X
| FIRE RESISTANCE RATING TABLE PER 2018 IBC TABLE 601 AND 602 | [6 empty] | X | X
| GENERAL NOTES AND SYMBOLS (REVISE TEMPLATE FOR PROJECT) | [6 empty] | X | X
| EXTERIOR OPENINGS CALCULATION TABLE (2018 IBC 705.8) | [8 empty] | X | X
|  | BUILDING KEY PLAN WITH ELEVATION TAGS | [7 empty] | X | X
| CODE ANALYSIS | [8 empty] | X | X |  |  | X | X
| FIRE/SMOKE INT/EXT WALL & FLOOR/ROOF ASSEMBLIES LEGEND | [6 empty] | X | X
|  | COORDINATE DETAIL REFERENCES | [9 empty] | X | X
| THERMAL ENVELOPE VALUES | [10 empty] | X | X
| UPDATE GENERAL NOTES AND SYMBOLS | [12 empty] | X | X

## A2.xx UNIT
MODEL HEALTH CHECKLIST |  | PASS | FAIL | COMMENTS | VIEW | ASSIGNED TO | STATUS
x
RVT UNIT LINKS (INSIDE THE LINK)
ALL UNIT ELEMENTS ARE SET TO THE CORRECT WORKSETS PER ORB STANDARDS
WALL PARAMETERS ARE FILLED OUT AND TAGS SHOWN CORRECTLY ON FLOOR PLANS
ENLARGED UNIT PLAN LINKS
UNIT LINKS ARE SET TO WORKSET "ENLARGED UNIT"
UNIT LINKS ARE NAMED " UNIT XX"
UNIT LINKS NAMES ARE LOWER THAN 100
UNIT LINKS HAVE CORRESPONDING SCOPE BOXES
UNIT LINKS SCOPE BOXES ARE NAMED "UNIT XX" WITH CAPITAL LETTERS
EXTERIOR GROUPS ARE SET TO "ENLARGED UNIT" WORKSET
ENLARGED UNIT SHEETS DRAWINGS
UNIT DRAWINGS ARE NAMED PER ORB STANDARDS NAMING CONVENTIONS
UNIT FLOOR PLANS HAVE THE "A2 ENLARGED UNIT PLANS" TEMPLATE ASSIGNED
UNIT ANSI DRAWINGS HAVE THE "A2 ENLARGED UNIT PLANS - ANSI" TEMPLATE ASSIGNED
UNIT ELEVATIONS HAVE THE "A2 INTERIOR ELEVATION" TEMPLATE ASSIGNED
BUILDING UNIT LINKS
UNIT LINKS ARE ASSIGNED TO THE "BUILDING LINKED UNITS" WORKSET
UNIT LINKS NAMES ARE SET TO THE UNIT ADDRESS NUMBER - NUMBER MUST BE HIGHER THAN 100
UNIT LINKS TYPE PARAMETER "RVT_UNIT COUNT" IS SET TO 1 ON ALL UNIT LINK TYPES
UNIT LINKS TYPE PARAMETER " RVT_NO. BEDROOMS" IS FILLED OUT PER UNIT DESIGN
UNIT LINKS TYPE PARAMETER " RVT_UNIT PLACED ON SHEET #" IS FILLED OUT PER UNIT SHEETS
UNIT LINKS TYPE PARAMETER "RVT_UNIT TYPE" IS FILLED OUT PER UNIT TYPE NAME
UNIT LINKS TYPE PARAMETER "RVT_UNIT ORDER" IS FILLED OUT PER ORB STANDARDS"UNIT LINKS - TAGS AND SCHEDULES BASICS"
GENERAL BUILDING MODELING
ROOF ELEMENTS ARE SET TO THE "ROOF PLAN" WORKSET
SLAB PLAN LINEWORK IS SET TO THE " SLAB PLANS" WORKSET
CONSULTANT MODELS ARE SET TO A SEPARATE WORKSET
CONSULTANT MODEL WORKSETS ARE SET TO NOT VISIBLE IN ALL VIEW IN WORKSET MANAGER
LANDSCAPE CAD FILES ARE SET TO THE " HARDSCAPE" WORKSET
CONSULTANT CAD FILES ARE SET TO A CLOSED WORKSET
CAD FILES ARE LINKED, NEVER INSERTED
OUTDATED CAD FILES ARE PURGED FROM THE PROJECT
UN-PLACED VIEWS ARE PURGED OUT OF THE PROJECT (EXCEPT WORKING VIEWS)
SURVEY MODEL IS SET TO NOT VISIBLE IN ALL VIEW IN WORKSET MANAGER - ONLY TURNED ON IN SITE VIEWS
UN-APPROVED FAMILIES ARE REVIEWED OR REPLACED FOR SIMPLER GEOMETRY FAMILIES
TEXT STYLES ARE ORB STANDARDS
DIMENSION STYLES ARE ORB STANDARD
LINE TYPES ARE ORB STANDARDS
VIEW TEMPLATES ARE ORB STANDARD
VIEWS ARE SET TO CORRESPONDING PROJECT BROWSER LOCATION
ENLARGED PLANS ARE SET TO CORRESPONDING SCOPE BOX, NAME "AREA X, AREA XX"
REVIT PHASES ARE ONLY AS REQUIRED, TYPICAL EXISTING AND NEW
SYSTEM FAMILY ASSEMBLIES ARE FROM HIVE DATABASE
WALLS
DOORS
WINDOWS
FLOORS
ROOFS
CEILINGS
QA/QC SYSTEM FAMILY SCHEDULES ARE FILLED OUT CORRECTLY
REPEATED FAMILIES ARE NOT PRESENT
ONLY MATERIALS IN USE
KEYNOTES ARE PER ORB MASTER KEYNOTE LIST
KEY SCHEDULE FOR LIFE SAFETY CORRESPONDS TO CONSTRUCTION TYPE AND APPLICABLE IBC VERSION
ELEVATIONS AND WALL SECTIONS
RVT_LINKS ARE TURNED OFF ON VIEWS THAT UNIT REFERENCES ARE NOT REQUIRED
AUTODESK CONSTRUCTION CLOUD DATA MANAGEMENT
THERE IS A PLOT SET SELECTED FOR CLOUD PUBLISH
CLOUD PUBLISH CORRESPONDS TO CURRENT PROJECT SHEETS
CLOUD PUBLISH 3D VIEW WITH UNITS
CLOUD PUBLISH 3D VIEW WITHOUT UNITS