## Complete Proj Checklist
Complete Project Checklist
GENERAL |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
GENERAL/PROJECT MANAGEMENT
PROJECT SCHEDULE |  |  | X | X
SHEET INDEX |  |  | X | X
ADDRESSING PLAN
SUBMITT | [6 empty] | X | X
APPROVAL | [8 empty] | X | X
SCHEDULE ORB TEAM MEETINGS |  |  | X | X
BUILDING KEY PLAN |  |  |  |  | X | X
DESIGN CHECKLIST |  |  |  |  | X | X
A1.xx SITE PLAN |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
SITE PLAN MODELING
ALTA SURVEY BACKGROUND |  |  | X | X
BUILDINGS OUTLINE |  |  | X | X
SITE HARDLINE |  |  | X | X
DIMENSIONS |  |  | X | X
VICINITY MAP |  |  | X | X
DEVELOPMENT DATA |  |  | X | X
UNIT MIX |  |  | X | X
SETBACKS |  |  | X | X
ZONING |  |  | X | X
BLDG AREAS |  |  | X | X
OPEN SPACE |  |  | X | X
LOT COVERAGE |  |  | X | X
FULL PARKING CALCULATIONS |  |  | X | X
LEGEND |  |  | X | X
GENERAL NOTES |  |  | X | X
LEGAL DESCRIPTION |  |  | X | X
KEYNOTES |  |  | X | X
ACCESSIBLE ROUT AND PARKING |  |  | X | X
OTHER (INFORMATION MAY VARY PER MUNICIPALITY) |  |  | X | X
SOLID WASTE NARRATIVE |  |  | X | X
FIRE AND TRASH TURNING RADIUS (CHECK CITY STANDARD) |  |  | X | X
FIRE HYDRANT COORDINATION |  |  | X | X | X | X
TRANSFORMERS/SWITCH GEAR COORDINATION W/ELECTRICAL |  |  |  |  | X | X
A1.xx LIFE SAFETY COVER |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
LIFE SAFETY KEY PLAN
KEY PLAN | [6 empty] | X | X
BLDG NUMBER | [6 empty] | X | X
|  | SECTION TAG |  |  |  |  | X | X
FIRE WALL LABELS | [6 empty] | X | X
ORB TITLE & NORTH ARROW | [6 empty] | X | X
LIFE SAFETY KEY SECTION
SECTION | [6 empty] | X | X
COLOR CODE OF FIRE ASSEMBLIES (WALLS, FLOOR-CEILING AND ROOF- CEILING) | [6 empty] | X | X
|  | BLDG NUMBER AND OCCUPANCY TYPE |  |  |  |  | X | X
BUILDING LEVELS AND GRADE LEVEL | [6 empty] | X | X
CONSTRUCTION TYPE | [6 empty] | X | X
EXIT DISCHARGE LEVEL | [6 empty] | X | X
CALLOUT OCCUPANCY SEPARATION (SEPARATED USE, NON-SEPARATED USE, ACCESSORY USE, ETC) | [6 empty] | X | X
FIRE WALL LABELS | [6 empty] | X | X
FLAME SPREAD AND FINISHES FIRE CLASSIFICATION (IBC 803.11) | [6 empty] | X | X
ACCESIBILITY COMPLIANCE | [6 empty] | X | X
OCCUPANT LOAD ANALYSIS PER BUILDING | [6 empty] | X | X
OCCUPANT LOAD ANALYSIS PER COURTYARD AREA | [6 empty] | X | X
BUILDING AREA ANALYSIS | [6 empty] | X | X
BUILDING CODES LIST | [6 empty] | X | X
FIRE RESISTANCE RATING TABLE PER 2018 IBC TABLE 601 AND 602 | [6 empty] | X | X
GENERAL NOTES AND SYMBOLS (REVISE TEMPLATE FOR PROJECT) | [6 empty] | X | X
EXTERIOR OPENINGS CALCULATION TABLE (2018 IBC 705.8) | [8 empty] | X | X
BUILDING KEY PLAN WITH ELEVATION TAGS | [8 empty] | X | X
CODE ANALYSIS | [8 empty] | X | X |  |  | X | X
FIRE/SMOKE INT/EXT WALL & FLOOR/ROOF ASSEMBLIES LEGEND | [6 empty] | X | X
COORDINATE DETAIL REFERENCES | [10 empty] | X | X
THERMAL ENVELOPE VALUES | [10 empty] | X | X
UPDATE GENERAL NOTES AND SYMBOLS | [12 empty] | X | X
A1.5x LIFE SAFETY PLANS - OVERALL BLDG PLANS |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
LIFE SAFETY PLAN MODELING
EXIT PASSAGEWAY |  |  |  |  | X | X
HORIZONTAL EXITS |  |  |  |  | X | X
LOCATE FDC (STAND PIPE) NEXT TO FIRE WALL AS NEEDED | [6 empty] | X | X
MODEL FIRE WALLS, CORRIDOR DOORS, AND MISC. ITEMS AS REQUIRED | [6 empty] | X | X
IMAGINARY PROPERTY LINE | [6 empty] | X | X
PLACE CORRIDOR FIRE EXTINGUISHER (IBC TABLE 906.3(1)) | [10 empty] | X | X
EXIT SIGN LOCATIONS (COORDINATE WITH ELECTRICAL) | [10 empty] | X | X
SHEET DESIGN
SYMBOLS (REVISE TEMPLATE FOR PROJECT) | [6 empty] | X | X
FIRE/SMOKE INT/EXT WALL & FLOOR/ROOF ASSEMBLIES LEGEND | [6 empty] | X | X
BUILDING KEY PLAN | [6 empty] | X | X
ORB TITLE, GRAPHIC SCALE & NORTH ARROW | [6 empty] | X | X
LIFE SAFETY SECTIONS | [6 empty] | X | X
OPEN PARKING GARAGE CALCULATION (2018 IBC 406.5.2) WHERE OCCURS | [6 empty] | X | X
UPDATE FIRE/SMOKE INT/EXT WALL & FLOOR/ROOF ASSEMBLIES LEGEND | [10 empty] | X | X
UPDATE OPEN PARKING GARAGE CALCULATION (2018 IBC 406.5.2) WHERE OCCURS | [10 empty] | X | X
LIFE SAFETY PLAN ANNOTATIONS
EXIT TRAVEL DISTANCE (IBC 1016.1) | [6 empty] | X | X
COMMON PATH OF EGRESS TRAVEL (IBC TABLE 1006.2.1) | [6 empty] | X | X
EXIT TRAVEL DEAD-END (50'-0" MAX.) (IBC SECTION 903.3.1.1 PER IBC 1020.4 EXP .2) | [6 empty] | X | X
STANDPIPE TRAVEL DISTANCE (905.4.6) | [6 empty] | X | X
LENGTH OF TRAVEL DISTANCE LABELS | [6 empty] | X | X
TRAVEL DISTANCE TO FIRE EXTINGUISHER (IBC TABLE 906.3(1)) | [10 empty] | X | X
LENGTH OF FIRE EXTINGUISHER TRAVEL DISTANCE LABELS | [10 empty] | X | X
LOCATE EXIT SIGN SYMBOLS | [10 empty] | X | X
DIMENSIONS
DISTANCE BETWEEN IMAGINARY PROPERTY LINE AND BUILDING EXTERIOR WALLS | [10 empty] | X | X
FIRE WALL AREA OF NO PENETRATION DIMENSION | [10 empty] | X | X
A1.5x LIFE SAFETY PLANS - OVERALL BLDG PLANS |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
KEYNOTES
CREATE KEYNOTES LIST | [6 empty] | X
UPDATE KEYNOTES LIST | [8 empty] | X | X | X | X | X | X
PLACE KEYNOTES ON BUILDING PLANS | [8 empty] | X | X | X | X | X | X
ADD DETAIL REFERENCE TO KEYNOTES | [10 empty] | X | X
UPDATE DETAIL REFERENCE TO KEYNOTES | [12 empty] | X | X
A1.5x LIFE SAFETY PLANS - ENLARGED BLDG PLANS |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
LIFE SAFETY PLAN MODELING
COLOR FILL ON LIFE SAFETY PLAN FOR OCCUPANCY CLASSIFICATION | [6 empty] | X | X
COLOR FILL ON LIFE SAFETY PLAN FOR FIRE/SMOKE WALL ASSEMBLIES | [6 empty] | X | X
SHEET DESIGN
SYMBOLS (REVISE TEMPLATE FOR PROJECT) | [6 empty] | X | X
FIRE/SMOKE INT/EXT WALL & FLOOR/ROOF ASSEMBLIES LEGEND | [6 empty] | X | X
BUILDING KEY PLAN | [6 empty] | X | X
SPLIT BLDG VIEWS AND ADD MATCH LINES | [6 empty] | X | X
ORB TITLE, GRAPHIC SCALE & NORTH ARROW | [6 empty] | X | X
LIFE SAFETY SECTIONS | [6 empty] | X | X
OPEN PARKING GARAGE CALCULATION (2018 IBC 406.5.2) WHERE OCCURS | [6 empty] | X | X
UPDATE FIRE/SMOKE INT/EXT WALL & FLOOR/ROOF ASSEMBLIES LEGEND | [10 empty] | X | X
UPDATE OPEN PARKING GARAGE CALCULATION (2018 IBC 406.5.2) WHERE OCCURS | [10 empty] | X | X
A1.5x LIFE SAFETY PLANS - ENLARGED BLDG PLANS |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
LIFE SAFETY PLAN ANNOTATIONS
ROOM NAMES W/NUMBER |  |  |  |  | X | X
PANIC HARDWARE SYMBOL AT DOORS | [6 empty] | X | X
AREA LABEL (AREA NAME, OCCUPANCY GROUP, AREA S.F. AND OCCUPANT LOAD) | [6 empty] | X | X
ACCESSIBLE UNIT LABEL | [6 empty] | X | X
MEANS OF EGRESS LABEL FOR DOORS (DOOR, EXIT WIDTH PROVIDED, MAX. OCCUPANT LOAD CAPACITY (2018 IBC 1005.3.2 EXP. 1), ACTUAL OCCUPANT LOAD, OPENING PROTECTION RATING (2018 IBC TABLE 716.1(2)) | [8 empty] | X | X
MEANS OF EGRESS LABEL FOR STAIRS (STAIR, EXIT WIDTH PROVIDED, MAX. OCCUPANT LOAD CAPACITY (2018 IBC 1005.3.1 EXP.1), ACTUAL OCCUPANT LOAD) | [8 empty] | X | X
WALL TYPE TAGS | [10 empty] | X | X
DETAIL CALLOUTS | [10 empty] | X | X
HORIZONTAL EXIT REFUGE AREA HATCH AND CALCULATIONS NOTE WITH CODE REFERENCE (2018 IBC 1026.4) | [10 empty] | X | X
ADD NOTE CALLOUT TO ALL STANDPIPES | [10 empty] | X | X
| HORIZONTAL EXIT INFORMATION | [9 empty] | X | X
EXIT PASSAGEWAY HATCH (2-HR FIRE BARRIER WALLS & 2-HR HORZ. ASSEMBLY) | [10 empty] | X | X
ADD OCCUPANT LOAD CALCULATION NEXT TO STAIR TAGS | [10 empty] | X | x
DIMENSIONS
DIAGONAL DISTANCE AND DOOR TO DOOR DISTANCE (WHEN MORE THAN ONE DOOR REQUIRED FROM ONE SPACE) | [10 empty] | X | X
FIRE WALL AREA OF NO PENETRATION DIMENSION | [10 empty] | X | X
EXIT TRAVEL DEAD-END TAGS | [10 empty] | X | X
KEYNOTES
CREATE KEYNOTES LIST | [6 empty] | X
UPDATE KEYNOTES LIST | [8 empty] | X | X | X | X | X | X
PLACE KEYNOTES ON BUILDING PLANS | [8 empty] | X | X | X | X | X | X
ADD DETAIL REFERENCE TO KEYNOTES | [10 empty] | X | X
UPDATE DETAIL REFERENCE TO KEYNOTES | [12 empty] | X | X
A2.xx UNIT PLANS (1/4"=1'-0") |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
UNIT PLAN MODELING
UNIT AREAS |  |  | X | X
DESIGN AND MODELING:
FURNITURE |  |  | X | X
KITCHEN, CLOSETS & ELECTRICAL EQUIPMENT |  |  | X | X
BATHROOM (TOILET, TUB, SHOWER, VANITY & MED. CABINET) |  |  | X | X
BATHROOM ACCESSORIES (TOILET PAPER HOLDERS/TOWEL BARS/ETC.) |  |  | X | X
BALCONIES W/RAIL (PATIOS AT 1ST LEVEL) |  |  | X | X
ANSI TYPE 'A' UNITS |  |  |  |  | X | X
ANSI TYPE 'B' UNITS |  |  |  |  | X | X
DROP CEILINGS (COORDINATE W/ MECHANICAL) | [10 empty] | X | X
SHEET DESIGN
LAYOUT UNITS ON 8.5"x11" W/ OVERALL DIMENSIONS AND AREAS |  |  | X | X
LAYOUT UNIT ON SHEET |  |  |  |  | X | X
LAYOUT ANSI UNIT PLAN ON SHEET |  |  |  |  | X | X
LAYOUT MOD UNITS ON SHEET |  |  |  |  | X | X
TITLE & GRAPHIC SCALE |  |  |  |  | X | X
GENERAL NOTES AND SYMBOLS (REVISE TEMPLATE FOR PROJECT) | [6 empty] | X | X
PLACE INTERIOR ELEVATIONS ON SHEET | [6 empty] | X | X
PLACE KEYNOTE SCHEDULE | [6 empty] | X | X
PLACE DOOR SCHEDULE ON SHEET | [8 empty] | X | X
PLACE WINDOW SCHEDULE ON SHEET | [8 empty] | X | X
UPDATE GENERAL NOTES AND SYMBOLS | [8 empty] | X | X | X | X | X | X
UNIT PLAN ANNOTATIONS
ROOM NAMES W/SIZES |  |  | X | X
ROOM NAMES (ONLY) | [6 empty] | X | X
INTERIOR ELEVATION TAGS | [8 empty] | X | X
VERIFY VANITY, SHOWER & TUB SIZE NOTES | [8 empty] | X | X
DOOR TAGS | [10 empty] | X | X
WINDOW TAGS | [10 empty] | X | X
WALL TYPE TAGS | [10 empty] | X | X
A2.xx UNIT PLANS (1/4"=1'-0") |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
DIMENSIONS
OVERALL DIMENSIONS | [6 empty] | X | X
PERIMETER DIMENSIONS | [8 empty] | X | X
INTERIOR DIMENSIONS (100% FINAL) | [10 empty] | X | X | X | X
KEYNOTES
CREATE KEYNOTES LIST |  |  |  |  | X | X
UPDATE KEYNOTES LIST | [6 empty] | X | X | X | X | X | X | X | X
ADD DETAIL REFERENCE TO KEYNOTES | [8 empty] | X | X
UPDATE DETAIL REFERENCE TO KEYNOTES | [8 empty] | X | X | X | X | X | X
PLACE KEYNOTES ON UNIT PLAN | [10 empty] | X | X
PLACE KEYNOTES ON ANSI PLAN | [10 empty] | X | X
ANSI UNIT PLANS
CLEAR FLOOR SPACES | [6 empty] | X | X
ACCESIBLE ROUTE | [6 empty] | X | X
TURNING SPACE IN ALL ROOMS IN ANSI TYPE 'A' UNITS | [6 empty] | X | X
CRITICAL DIMENSIONS & NOTES | [6 empty] | X | X
PLACE GENERAL KEYNOTES | [10 empty] | X | X
PLACE ANSI TYPE 'A' KEYNOTES AT ANSI TYPE 'A' UNITS ONLY | [10 empty] | X | X
INTERIOR ELEVATIONS
CREATE VIEWS AND PLACE ON SHEET |  |  |  |  | X | X
DIMENSIONS & NOTES | [10 empty] | X | X
PLACE GENERAL KEYNOTES | [10 empty] | X | X
PLACE ANSI TYPE 'A' KEYNOTES AT ANSI TYPE 'A' UNITS ONLY | [10 empty] | X | X
DOOR SCHEDULE
CREATE DOOR SCHEDULE | [6 empty] | X | X
DOOR TYPES SCHEDULE ELEVATION FROM TEMPLATE | [6 empty] | X | X
DOOR HARDWARE | [6 empty] | X | X
WINDOW SCHEDULE
CREATE WINDOW SCHEDULE | [6 empty] | X | X
WINDOW TYPES FROM TEMPLATE | [6 empty] | X | X
A3.xx BUILDING PLANS |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
BUILDING PLAN MODELING
DESIGN AND MODELING:
PARKING SPACES WITH STRIPES |  |  | X | X
ACCESSIBLE PARKING SPACES |  |  | X | X
GARAGE VENTILATION SHAFT AS NEEDED |  |  | X | X |  |  | X | X
GRID LINES (COLUMNS, CONCRETE AND CMU WALLS) |  |  |  |  | X | X
VERIFY AND COORDINATE GARAGE RAMPS DESIGN |  |  |  |  | X | X
CORRIDORS RCP |  |  |  |  | X | X
ANCILLARY SPACES (CORRIDOR STORAGE, A/C, ELEVATOR LOBBY, ETC) |  |  |  |  | X | X | X | X
MAIL BOXES AND PARCEL LOCKERS/STORAGE | [6 empty] | X | X
VERTICAL CIRCULATIONS (STAIRS AND ELEVATORS) | [6 empty] | X | X
COMMON AREAS (LEASING, REC, FITNESS, ETC) | [6 empty] | X | X
COORDINATE COLUMNS AND SHEARWALLS WITH STRUCTURAL | [6 empty] | X | X | X | X | X | X
SHEET DESIGN
BUILDING KEY PLAN |  |  |  |  | X | X
SPLIT BLDG VIEWS AND ADD MATCH LINES |  |  |  |  | X | X
ORB TITLE, GRAPHIC SCALE & NORTH ARROW |  |  |  |  | X | X
GENERAL NOTES AND SYMBOLS (REVISE TEMPLATE FOR PROJECT) | [6 empty] | X | X
PLACE KEYNOTE SCHEDULE | [6 empty] | X | X
UPDATE GENERAL NOTES AND SYMBOLS | [6 empty] | X | X | X | X | X | X | X | X
INSULATION SCHEDULE | [10 empty] | X | X
A3.xx BUILDING PLANS |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
BUILDING PLAN ANNOTATIONS
REVIEW OVERALL BUILDING ELEVATION TAGS |  |  | X | X
ROOM NAMES W/NUMBER |  |  |  |  | X | X
GRIDLINES |  |  |  |  | X | X
TYPE A UNIT SYMBOLS |  |  |  |  | X | X
PLACE FIRE WALL SYMBOL |  |  |  |  | X | X
ENLARGED PLAN CALLOUTS | [6 empty] | X | X
REVIEW ENLARGED BUILDING ELEVATION TAGS | [6 empty] | X | X
TRASH CHUTE CARTS AND MISCELLANEOUS ITEMS | [6 empty] | X | X
REVIEW BUILDING SECTION TAGS (LOOKING PLAN NORTH AND EAST) | [6 empty] | X | X |  |  | X | X
COMMONS/CORRIDORS DOOR TAGS | [8 empty] | X | X
COMMONS/CORRIDORS WINDOW TAGS | [8 empty] | X | X
COMMONS/CORRIDORS STOREFRONT TAGS | [8 empty] | X | X
REVIEW WALL SECTION TAGS (LOOKING PLAN NORTH AND EAST) | [10 empty] | X | X
WALL TYPE TAGS | [10 empty] | X | X | X | X
DETAIL CALLOUTS | [10 empty] | X | X | X | X
DIMENSIONS
GRIDLINES DIMENSIONS | [6 empty] | X | X
DRIVEWAY & PARKING SPACES DIMENSIONS | [8 empty] | X | X
PERIMETER DIMENSIONS (OVERALL PLAN) | [10 empty] | X | X
FULLY DIMENSION ENLARGED BUILDING PLANS | [10 empty] | X | X
KEYNOTES
CREATE KEYNOTES LIST | [6 empty] | X | X
UPDATE KEYNOTES LIST | [8 empty] | X | X | X | X | X | X
PLACE KEYNOTES ON BUILDING PLANS | [8 empty] | X | X | X | X | X | X
ADD DETAIL REFERENCE TO KEYNOTES | [10 empty] | X | X
UPDATE DETAIL REFERENCE TO KEYNOTES | [12 empty] | X | X
A3.xx REFLECTED CEILING PLANS (1/8"=1'-0") |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
REFLECTED CEILING PLAN MODELING
SHOW WALLS, DOORS & WINDOWS (HALFTONE) | [8 empty] | X | X
TURN OFF EVERYTHING ELSE IN THE UNIT | [8 empty] | X | X
SHOW ROOF HATCH & ATTICC ACCESS | [8 empty] | X | X
DROPPED CEILING AT CORRIDORS AND ANCILLARY SPACES | [8 empty] | X | X
COORDINATE COORRIDOR CROSSINGS WITH PLUMBING (TEAL SYSTEM) | [8 empty] | X | X
DRAW LIGHTS (COORDINATE W/ELECTRICAL) | [10 empty] | X | X
DRAW EXIT SIGNS (COORDINATE W/ELECTRICAL) | [10 empty] | X | X
SHEET DESIGN
BUILDING KEY PLAN | [8 empty] | X | X
MATCH LINE | [8 empty] | X | X
ORB TITLE, GRAPHIC SCALE & NORTH ARROW | [8 empty] | X | X
PLACE KEYNOTE SCHEDULE | [8 empty] | X | X
REFLECTED CEILING PLAN ANNOTATIONS
CEILING HEIGHT TAG | [10 empty] | X | X
UNIT AND COMMON AREAS NAMES AND NUMBER | [10 empty] | X | X
REFERENCE SHEET FOR COMMON AREAS RCP | [10 empty] | X | X
CEILING DIMENSIONS | [10 empty] | X | X
KEYNOTES
CREATE KEYNOTES LIST | [10 empty] | X | X
PLACE KEYNOTES | [10 empty] | X | X
ADD DETAIL REFERENCE TO KEYNOTES | [10 empty] | X | X
UPDATE KEYNOTES LIST | [12 empty] | X | X
UPDATE DETAIL REFERENCE TO KEYNOTES | [12 empty] | X | X
A3.xx ROOF PLANS (1/8"=1'-0") |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
ROOF PLAN MODELING
DESIGN AND MODELING:
PARAPETS |  |  | X | X
CANOPIES AND LOWER ROOFS |  |  | X | X
ROOF SLOPES (COORDINATE STRUCTURAL FRAMING) |  |  |  |  | X | X
ROOF CRICKETS, ROOF DRAINS, SCUPPERS, ETC. |  |  |  |  | X | X
ROOF SEPARATION CURB |  |  |  |  | X | X
A/C EQUIPMENT AND SERVICE WALLS |  |  |  |  | X | X
SHOW TOP FLOOR WALLS IN HALF TONE |  |  |  |  | X | X
SHOW GRID LINE |  |  |  |  | X | X
FIRE WALLS AT ROOF | [6 empty] | X | X
STAIR AND ELEVATOR TOWERS | [6 empty] | X | X
ROOF VENTS AS NEEDED | [8 empty] | X | X
ROOF ACCESS HATCH | [8 empty] | X | X
CORRIDOR AIR CONDITIONING UNIT FRESH AIR SHAFT AT ROOF | [8 empty] | X | X
TRASH CHUTE EXHAUST FAN | [8 empty] | X | X
ELEVATOR SHAFT AIR CONDITIONING UNIT | [8 empty] | X | X
STANDPIPE AT ROOF | [8 empty] | X | X
SHEET DESIGN
GENERAL NOTES AND SYMBOLS (REVISE TEMPLATE FOR PROJECT) |  |  |  |  | X | X
MATCH LINES |  |  |  |  | X | X
ORB TITLE, GRAPHIC SCALE & NORTH ARROW |  |  |  |  | X | X
BUILDING KEY PLAN |  |  |  |  | X | X
UPDATE GENERAL NOTES AND SYMBOLS | [10 empty] | X | X
A3.xx ROOF PLANS (1/8"=1'-0") |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
ROOF PLAN ANNOTATIONS
REFERENCE MATCH LINE |  |  |  |  | X | X
SLOPE ARROWS | [6 empty] | X | X
FIRE WALL SYMBOL | [6 empty] | X | X
FIRE WALL AREA OF NO PENETRATION HATCH | [6 empty] | X | X
UNIT NAMES AND NUMBER | [6 empty] | X | X
PARAPETS SPOT ELEVATION | [10 empty] | X | X
DETAIL CALLOUTS | [10 empty] | X | X
ENLARGED PLANS CALLOUTS | [10 empty] | X | X
REVIEW SECTION TAGS | [10 empty] | X | X
DIMENSIONS
FIRE WALL NO OPENINGS AREA DIMENSION | [6 empty] | X | X
KEYNOTES
CREATE KEYNOTES LIST | [6 empty] | X | X
UPDATE KEYNOTES LIST | [10 empty] | X | X
PLACE KEYNOTES ON ROOF PLANS | [10 empty] | X | X
ADD DETAIL REFERENCE TO KEYNOTES | [10 empty] | X | X
UPDATE DETAIL REFERENCE TO KEYNOTES | [12 empty] | X | X
A3.xx BUILDING ELEVATIONS |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
BUILDING ELEVATIONS MODELING
SHOW:
TOWERS, CANOPIES, PARAPETS AND BANDS |  |  | X | X
WINDOWS, DOORS, STOREFRONTS AND BALCONY RAILINGS |  |  | X | X
MATERIAL TEXTURES (HARDIE, BRICK VENEER, BLOCK, ETC.) |  |  | X | X
SCUPPERS AT BALCONIES | [6 empty] | X | X
CREATE ENLARGED ELEVATION VIEWS | [6 empty] | X | X
BUILDING MOUNTED UTILITIES (S.E.S., METERS, ETC) | [6 empty] | X | X
SHEET DESIGN
ORB TITLE & GRAPHIC SCALE |  |  | X | X
MATERIAL /COLOR KEYNOTES |  |  | X | X
BUILDING KEY PLAN |  |  |  |  | X | X
GENERAL NOTES (REVISE TEMPLATE FOR PROJECT) | [6 empty] | X | X
UPDATE GENERAL NOTES | [12 empty] | X | X
BUILDING ELEMENTS
DASH IN A/C UNITS ON ROOF | [6 empty] | X | X
BUILDING MOUNTED SIGNS | [6 empty] | X | X |  |  | X | X
STUCCO JOINTS | [8 empty] | X | X
STUCCO EXPANSION JOINTS | [8 empty] | X | X
BUILDING EXPANSION JOINT (AS REQUIRED) | [8 empty] | X | X
THROUGH WALL VENTS | [10 empty] | X | X
BUILDING EXTERIOR LIGHTS | [10 empty] | X | X
BUILDING ELEVATION ANNOTATIONS
MATERIAL/COLOR TAGS |  |  | X | X
GRID LINES | [6 empty] | X | X
FIRE WALL AREA OF NO PENETRATION HATCH | [8 empty] | X | X
UNIT NAME REFERENCE LABEL | [8 empty] | X | X
DETAIL CALLOUTS | [10 empty] | X | X
REVIEW/UPDATE MATERIAL TAGS | [10 empty] | X | X
REVIEW SECTION TAGS | [10 empty] | X | X
A3.xx BUILDING ELEVATIONS |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
KEYNOTES
CREATE KEYNOTES LIST | [6 empty] | X | X
REVIEW/UPDATE KEYNOTES LIST | [10 empty] | X | X
PLACE KEYNOTES | [10 empty] | X | X
ADD DETAIL REFERENCE TO KEYNOTES | [10 empty] | X | X
REVIEW/UPDATE DETAIL REFERENCE TO KEYNOTES | [12 empty] | X | X
A4.xx BUILDING SECTIONS (1/16"=1'-0") |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
MODELING
FOUNDATION (COORDINATE WITH STRUCTURAL) | [8 empty] | X | X
SHEET DESIGN
BUILDING KEY PLAN | [6 empty] | X | X
LAYOUT BLDG SECTIONS ON SHEET | [6 empty] | X | X
ORB TITLE & GRAPHIC SCALE | [6 empty] | X | X
BUILDING SECTION ANNOTATIONS
GRIDLINES | [6 empty] | X | X
ROOM NAMES W/NUMBER | [10 empty] | X | X
WALL SECTIONS CALLOUTS | [10 empty] | X | X
DETAIL CALLOUTS | [10 empty] | X | X
A4.xx WALL SECTIONS (3/8"=1'-0") |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
WALL SECTION MODELING
FOUNDATION (COORDINATE WITH STRUCTURAL) | [8 empty] | X | X
COORDINATE AND SHOW STRUCTURAL ELEMENTS (BEAMS, FRAMING, ETC) | [8 empty] | X | X
COORDINATE AND SHOW DROPPED CEILINGS | [8 empty] | X | X
SHEET DESIGN
BUILDING KEY PLAN | [6 empty] | X | X
LAYOUT WALL SECTIONS ON SHEET | [6 empty] | X | X
ORB TITLE & GRAPHIC SCALE | [6 empty] | X | X
WALL SECTION ANNOTATIONS
ROOM NAMES W/NUMBER | [8 empty] | X | X
GRIDLINES | [8 empty] | X | X
ANNOTATE BLDG COMPONENTS (FRAMING, INSULATION, FINISHES, ETC) | [8 empty] | X | X
DETAIL CALLOUTS | [10 empty] | X | X
KEYNOTES | [10 empty] | X | X
WALL TYPE TAGS | [10 empty] | X | X
FLOOR-CEILING TAGS | [10 empty] | X | X
ROOF-CEILING TAGS | [10 empty] | X | X
BALCONY/ROOF SLOPE ARROWS | [10 empty] | X | X
DIMENSIONS
DIMENSIONS TO TOP/BOTTOM POPOUTS | [10 empty] | X | X
DIMENSIONS TO LOW WALLS/GUARDRAILS | [10 empty] | X | X
DIMENSIONS TO CANOPIES | [10 empty] | X | X
DIMENSIONS TO ARCHITECTURAL FEATURES | [10 empty] | X | X
KEYNOTES
CREATE KEYNOTES LIST | [6 empty] | X | X
PLACE KEYNOTES ON SECTIONS | [10 empty] | X | X
ADD DETAIL REFERENCE TO KEYNOTES | [10 empty] | X | X
UPDATE KEYNOTES LIST | [10 empty] | X | X | X | X
UPDATE DETAIL REFERENCE TO KEYNOTES | [12 empty] | X | X
A5.00 SCHEDULES |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
CREATE SCHEDULES AND VIEWS
COMMONS DOOR SCHEDULE | [8 empty] | X | X
COMMONS DOOR TYPE ELEVATIONS (FROM TEMPLATE) | [8 empty] | X | X
COMMONS DOOR HARDWARE SCHEDULE (FROM TEMPLATE) | [8 empty] | X | X
COMMONS WINDOW SCHEDULE | [8 empty] | X | X
COMMONS WINDOW TYPE ELEVATIONS | [8 empty] | X | X
STOREFRONT ELEVATIONS | [8 empty] | X | X
GATE SCHEDULE | [10 empty] | X | X
GATE ELEVATIONS | [10 empty] | X | X
SHEET DESIGN
SCHEDULES (DOORS, WINDOWS, GATES) | [8 empty] | X | X
DOORS AND WINDOWS GENERAL NOTES (REVISE TEMPLATE FOR PROJECT) | [8 empty] | X | X
DOOR ABBREVIATIONS | [8 empty] | X | X
PLACE DOOR TYPES ELEVATIONS | [8 empty] | X | X
PLACE WINDOW TYPES ELEVATIONS | [8 empty] | X | X
PLACE STOREFRONT TYPES ELEVATIONS | [8 empty] | X | X
PLACE HARDWARE SCHEDULE | [8 empty] | X | X
GATE CLEARANCE DETAIL | [8 empty] | X | X
UPDATE DOORS AND WINDOWS GENERAL NOTES | [10 empty] | X | X
A5.00 SCHEDULES |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
ANNOTATIONS AND COORDINATION
COORDINATE DOOR NUMBERS WITH ROOM NUMBERS | [8 empty] | X | X
REVIEW DOORS ARE MODELED CORRECTLY | [10 empty] | X | X
COORDINATE HARDWARE SET ON EACH DOOR | [10 empty] | X | X
VERIFY DOOR LOCATION (ROOM) | [10 empty] | X | X
VERIFY DOOR FIRE RATING | [10 empty] | X | X
COORDINATE WINDOW TYPES WITH SCHEDULE | [10 empty] | X | X
VERIFY ALL COMMONS WINDOWS ARE IN SCHEDULE | [10 empty] | X | X
VERIFY WINDOWS TEMPERED GLASS LOCATIONS | [10 empty] | X | X
DIMENSION EACH STOREFRONT ELEVATION | [10 empty] | X | X
ADD STOREFRONT DETAIL CALLOUTS | [10 empty] | X | X
ADD TEMPERED NOTATION TO EACH STOREFRONT GLASS PANEL AS REQUIRED | [10 empty] | X | X
COORDINATE GATE SCHEDULE WITH PROJECT | [10 empty] | X | X
A5.xx ENLARGED PLANS (COMMON AREAS, LEASING, REC, FITNESS, ETC) (1/4"=1'-0") |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
COMMON AREAS MODELING
REVIEW WINDOWS, DOORS & STOREFRONTS | [6 empty] | X | X
RESTROOM ACCESSORIES (TOILET PAPER HOLDERS/TOWEL BARS/ETC.) | [6 empty] | X | X
KITCHEN, COUNTERTOPS, ETC. (COORDINATE WITH I.D.) | [6 empty] | X | X
MAIL BOXES, PARCEL, ETC | [6 empty] | X | X
DROPPED CEILINGS (COORDINATE W/ MECHANICAL & INTERIOR DESIGN) | [8 empty] | X | X
RESTROOM (REVIEW AND COORDINATE WITH I.D.) | [8 empty] | X | X
INTERIOR ELEVATIONS | [8 empty] | X | X
COORDINATE SPECIALTY ITEMS WITH I.D. | [8 empty] | X | X
COORDINATE STRUCTURAL COMPONENTS | [8 empty] | X | X
SHEET DESIGN
GENERAL NOTES AND SYMBOLS (REVISE TEMPLATE FOR PROJECT) |  |  |  |  | X | X
ORB TITLE & GRAPHIC SCALE |  |  |  |  | X | X
KEYNOTES |  |  |  |  | X | X
PLACE INTERIOR ELEVATIONS ON SHEET (MAY BE A SEPARATE SHEET) | [6 empty] | X | X
UPDATE GENERAL NOTES AND SYMBOLS | [10 empty] | X | X
ENLARGED PLAN ANNOTATIONS
ROOM NAMES & NUMBER |  |  |  |  | X | X
GRIDLINES |  |  |  |  | X | X
APPLIANCE LABELS |  |  |  |  | X | X
CLEAR FLOOR SPACES (INCLUDING DOORS) | [6 empty] | X | X
DOOR TAGS | [8 empty] | X | X
WINDOW TAGS | [8 empty] | X | X
STOREFRONT TAGS | [8 empty] | X | X
INTERIOR ELEVATION TAGS | [8 empty] | X | X
ENLARGED PLANS CALLOUTS | [8 empty] | X | X
WALL TYPE TAGS | [10 empty] | X | X
DETAIL CALLOUTS | [10 empty] | X | X
REVIEW WALL SECTION TAGS | [10 empty] | X | X
A5.xx ENLARGED PLANS (COMMON AREAS, LEASING, REC, FITNESS, ETC) (1/4"=1'-0") |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
DIMENSIONS
DIMENSION ALL WALLS, WINDOWS, STOREFRONT, COLUMNS AND MISCELLANEOUS COMPONENTS | [10 empty] | X | X
CHECK AND REVIEW DIMENSIONS | [12 empty] | X | X
KEYNOTES
CREATE KEYNOTES LIST | [6 empty] | X | X
PLACE KEYNOTES ON ENLARGED PLANS | [10 empty] | X | X
ADD DETAIL REFERENCE TO KEYNOTES | [10 empty] | X | X
UPDATE KEYNOTES LIST | [10 empty] | X | X | X | X
UPDATE DETAIL REFERENCE TO KEYNOTES | [12 empty] | X | X
INTERIOR ELEVATIONS
CREATE VIEWS AND PLACE ON SHEET | [8 empty] | X | X
APPLIANCE LABELS | [10 empty] | X | X
DIMENSIONS | [10 empty] | X | X
DETAIL CALLOUTS | [10 empty] | X | X
PLACE KEYNOTES | [10 empty] | X | X
A6.xx ENLARGED PLANS (STAIR, ELEVATOR, TRASH CHUTE, ETC.) (1/4"=1'-0") |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
ENLARGED PLAN MODELING
STAIR/ELEVATOR/TRASH CHUTE SHAFTS |  |  | X | X
VERIFY EXIT PASSAGE WAYS AT GROUND LEVEL AS REQUIRED |  |  |  |  | X | X
STAIR, GUARDRAILS, HANDRAILS, ETC |  |  |  |  | X | X
VERTICAL CLEARANCE BARRIER |  |  |  |  | X | X
STAIR GATE AT DISCHARGE LEVEL IF NEEDED (2018 IBC 1023.8) |  |  |  |  | X | X
FURRING WALL | [6 empty] | X | X
STANDPIPE & STANDPIPE PROTECTION AT STAIR TOWERS | [6 empty] | X | X
STANDPIPE CABINET AT HORIZONTAL EXITS | [6 empty] | X | X
ROOF ACCESS (HATCH, LADDER) | [6 empty] | X | X
ELEVATOR CAB | [6 empty] | X | X
TRASH CHUTE SYSTEM & CHUTE DOOR | [6 empty] | X | X
CORRIDOR STORAGE, ELEVATOR LOBBY, ETC (ACCESSIBLE STORAGE) | [6 empty] | X | X
EMERGENCY RESPONDER RADIO COVERAGE SYSTEM (ERRC, 2018 IBC 918) | [6 empty] | X | X
ELEVATOR TOWER ROOF | [6 empty] | X | X
DROPPED CEILING (COORDINATE WITH MECHANICAL) | [8 empty] | X | X
CORRIDOR A/C UNITS AND FRESH AIR SHAFT | [8 empty] | X | X
ELECTRICAL METERS, IDF, MDF | [8 empty] | X | X
ELEVATOR DISCONNECT CLOSET (NORMALLY AT TOP LEVEL) | [8 empty] | X | X
ELEVATOR A/C AT ROOF | [8 empty] | X | X
ELEVATOR RECESSED PUMP PIT | [8 empty] | X | X
ELEVATOR PIT LADDER | [8 empty] | X | X
SHEET DESIGN
GENERAL NOTES AND SYMBOLS (REVISE TEMPLATE FOR PROJECT) | [6 empty] | X | X
UPDATE GENERAL NOTES AND SYMBOLS | [6 empty] | X | X
ORB TITLE & GRAPHIC SCALE | [6 empty] | X | X
KEYNOTES | [6 empty] | X | X
A6.xx ENLARGED PLANS (STAIR, ELEVATOR, TRASH CHUTE, ETC.) (1/4"=1'-0") |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
ENLARGED PLAN ANNOTATIONS
ROOM NAMES & NUMBER | [6 empty] | X | X
CLEAR FLOOR SPACES | [6 empty] | X | X
TURNING RADIUS | [6 empty] | X | X
DOOR TAGS | [10 empty] | X | X
WINDOW TAGS | [10 empty] | X | X
WALL TYPE TAGS | [10 empty] | X | X
DETAIL CALLOUTS | [10 empty] | X | X
STAIRS AND/OR RAMPS DN & UP ARROW | [10 empty] | X | X
REVIEW STAIR & ELEVATOR SECTION CALLOUTS | [10 empty] | X | X
DIMENSIONS
DIMENSION ALL WALLS, COLUMNS AND MISCELLANEOUS BLDG COMPONENTS | [10 empty] | X | X
STAIR INFORMATION (TREADS, RISERS, LANDING) | [10 empty] | X | X
ELEVATOR HOISTWAY DIMENSIONS | [10 empty] | X | X
CHUTE CENTERLINE | [10 empty] | X | X
DOOR OPENINGS AT CMU AND CONC. WALLS | [10 empty] | X | X
SUMP CENTERLINE AND SIZE | [10 empty] | X | X
CHECK AND REVIEW DIMENSIONS | [12 empty] | X | X
KEYNOTES
CREATE KEYNOTES LIST | [6 empty] | X | X
PLACE KEYNOTES ON ENLARGED PLANS | [10 empty] | X | X
ADD DETAIL REFERENCE TO KEYNOTES | [10 empty] | X | X
UPDATE KEYNOTES LIST | [10 empty] | X | X | X | X
UPDATE DETAIL REFERENCE TO KEYNOTES | [12 empty] | X | X
A6.xx STAIR/ELEV SECTIONS (1/4"=1'-0") |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
STAIR/ELEV SECTION MODELING
FOUNDATION (COORDINATE WITH STRUCTURAL) | [8 empty] | X | X
COORDINATE AND SHOW STRUCTURAL ELEMENTS (BEAMS, FRAMING, ETC) | [8 empty] | X | X
COORDINATE AND SHOW DROPPED CEILINGS | [8 empty] | X | X
CHUTE EXHAUST VENT | [8 empty] | X | X
SHEET DESIGN
GENERAL NOTES AND SYMBOLS (SAME AS ENLARGED PLANS) | [8 empty] | X | X
LAYOUT WALL SECTIONS ON SHEET | [8 empty] | X | X
ORB TITLE & GRAPHIC SCALE | [8 empty] | X | X
STAIR/ELEV SECTION ANNOTATIONS
ROOM NAMES W/NUMBER | [8 empty] | X | X
GRIDLINES | [8 empty] | X | X
DETAIL CALLOUTS | [10 empty] | X | X
KEYNOTES | [10 empty] | X | X
WALL TYPE TAGS | [10 empty] | X | X
FLOOR-CEILING TAGS | [10 empty] | X | X
ROOF-CEILING TAGS | [10 empty] | X | X
ANNOTATE BLDG COMPONENTS (FRAMING, INSULATION, FINISHES, ETC) | [10 empty] | X | X
ELEVATOR ROOF SLOPE ARROW | [10 empty] | X | X
DIMENSIONS
DIMENSION STAIR RISER | [10 empty] | X | X
DIMENSION WINDOWS AND/OR OPENINGS IF APPLICABLE | [10 empty] | X | X
ELEVATOR PIT/SUMP DEPTH | [10 empty] | X | X
ELEVATOR ROOF ELEVATIONS | [10 empty] | X | X
ELEVATOR OVERHEAD BEAM AND MIN. CEILING HEIGHT | [10 empty] | X | X
CLEARANCE TO CHUTE DISCHARGE OPENING | [10 empty] | X | X
A6.xx STAIR/ELEV SECTIONS (1/4"=1'-0") |  |  | PRELIM. |  | 50% DD |  | 100% DD |  | 50% CD |  | 75% CD |  | 100% CD
|  |  | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM | ASSOCIATE | PM
KEYNOTES
CREATE KEYNOTES LIST | [6 empty] | X | X
PLACE KEYNOTES ON SECTIONS | [10 empty] | X | X
ADD DETAIL REFERENCE TO KEYNOTES | [10 empty] | X | X
UPDATE KEYNOTES LIST | [10 empty] | X | X | X | X
UPDATE DETAIL REFERENCE TO KEYNOTES | [12 empty] | X | X

## Prelim
Preliminary Project Checklist
GENERAL | Assigned to | PRELIM.
|  | ASSOCIATE | PM
GENERAL/PROJECT MANAGEMENT
PROJECT SCHEDULE
SHEET INDEX
SCHEDULE ORB TEAM MEETINGS
A1.xx SITE PLAN | Assigned to | PRELIM.
|  | ASSOCIATE | PM
SITE PLAN MODELING
ALTA SURVEY BACKGROUND
BUILDINGS OUTLINE
SITE HARDLINE
DIMENSIONS
VICINITY MAP
DEVELOPMENT DATA
UNIT MIX
SETBACKS
ZONING
BLDG AREAS
OPEN SPACE
LOT COVERAGE
FULL PARKING CALCULATIONS
LEGEND
GENERAL NOTES
LEGAL DESCRIPTION
KEYNOTES
ACCESSIBLE ROUT AND PARKING
OTHER (INFORMATION MAY VARY PER MUNICIPALITY)
SOLID WASTE NARRATIVE
FIRE AND TRASH TURNING RADIUS (CHECK CITY STANDARD)
FIRE HYDRANT COORDINATION
A2.xx UNIT PLANS (1/4"=1'-0") | Assigned to | PRELIM.
|  | ASSOCIATE | PM
UNIT PLAN MODELING
UNIT AREAS
DESIGN AND MODELING:
FURNITURE
KITCHEN, CLOSETS & ELECTRICAL EQUIPMENT
BATHROOM (TOILET, TUB, SHOWER, VANITY & MED. CABINET)
BATHROOM ACCESSORIES (TOILET PAPER HOLDERS/TOWEL BARS/ETC.)
BALCONIES W/RAIL (PATIOS AT 1ST LEVEL)
SHEET DESIGN
LAYOUT UNITS ON 8.5"x11" W/ OVERALL DIMENSIONS AND AREAS
UNIT PLAN ANNOTATIONS
ROOM NAMES W/SIZES
A3.xx BUILDING PLANS | Assigned to | PRELIM.
|  | ASSOCIATE | PM
BUILDING PLAN MODELING
DESIGN AND MODELING:
PARKING SPACES WITH STRIPES
ACCESSIBLE PARKING SPACES
GARAGE VENTILATION SHAFT AS NEEDED
A3.xx BUILDING PLANS | Assigned to | PRELIM.
|  | ASSOCIATE | PM
BUILDING PLAN ANNOTATIONS
REVIEW OVERALL BUILDING ELEVATION TAGS
A3.xx ROOF PLANS (1/8"=1'-0") | Assigned to | PRELIM.
|  | ASSOCIATE | PM
ROOF PLAN MODELING
DESIGN AND MODELING:
PARAPETS
CANOPIES AND LOWER ROOFS
A3.xx BUILDING ELEVATIONS | Assigned to | PRELIM.
|  | ASSOCIATE | PM
BUILDING ELEVATIONS MODELING
SHOW:
TOWERS, CANOPIES, PARAPETS AND BANDS
WINDOWS, DOORS, STOREFRONTS AND BALCONY RAILINGS
MATERIAL TEXTURES (HARDIE, BRICK VENEER, BLOCK, ETC.)
SHEET DESIGN
ORB TITLE & GRAPHIC SCALE
MATERIAL /COLOR KEYNOTES
BUILDING ELEVATION ANNOTATIONS
MATERIAL/COLOR TAGS
A6.xx ENLARGED PLANS (STAIR, ELEVATOR, TRASH CHUTE, ETC.) (1/4"=1'-0") | Assigned to | PRELIM.
|  | ASSOCIATE | PM
ENLARGED PLAN MODELING
STAIR/ELEVATOR/TRASH CHUTE SHAFTS

## 50% DD
50% DD Checklist
GENERAL | Assigned to | 50% DD
|  | ASSOCIATE | PM
GENERAL/PROJECT MANAGEMENT
BUILDING KEY PLAN
DESIGN CHECKLIST
A1.xx SITE PLAN | Assigned to | 50% DD
|  | ASSOCIATE | PM
SITE PLAN MODELING
FIRE HYDRANT COORDINATION
TRANSFORMERS/SWITCH GEAR COORDINATION W/ELECTRICAL
A1.5x LIFE SAFETY PLANS - OVERALL BLDG PLANS | Assigned to | 50% DD
|  | ASSOCIATE | PM
LIFE SAFETY PLAN MODELING
EXIT PASSAGEWAY
HORIZONTAL EXITS
A1.5x LIFE SAFETY PLANS - ENLARGED BLDG PLANS | Assigned to | 50% DD
|  | ASSOCIATE | PM
LIFE SAFETY PLAN ANNOTATIONS
ROOM NAMES W/NUMBER
A2.xx UNIT PLANS (1/4"=1'-0") | Assigned to | 50% DD
|  | ASSOCIATE | PM
UNIT PLAN MODELING
ANSI TYPE 'A' UNITS
ANSI TYPE 'B' UNITS
SHEET DESIGN
LAYOUT UNIT ON SHEET
LAYOUT ANSI UNIT PLAN ON SHEET
LAYOUT MOD UNITS ON SHEET
TITLE & GRAPHIC SCALE
A2.xx UNIT PLANS (1/4"=1'-0") | Assigned to | 50% DD
|  | ASSOCIATE | PM
KEYNOTES
CREATE KEYNOTES LIST
INTERIOR ELEVATIONS
CREATE VIEWS AND PLACE ON SHEET
A3.xx BUILDING PLANS | Assigned to | 50% DD
|  | ASSOCIATE | PM
BUILDING PLAN MODELING
DESIGN AND MODELING:
GRID LINES (COLUMNS, CONCRETE AND CMU WALLS)
VERIFY AND COORDINATE GARAGE RAMPS DESIGN
CORRIDORS RCP
ANCILLARY SPACES (CORRIDOR STORAGE, A/C, ELEVATOR LOBBY, ETC)
SHEET DESIGN
BUILDING KEY PLAN
SPLIT BLDG VIEWS AND ADD MATCH LINES
ORB TITLE, GRAPHIC SCALE & NORTH ARROW
A3.xx BUILDING PLANS | Assigned to | 50% DD
|  | ASSOCIATE | PM
BUILDING PLAN ANNOTATIONS
ROOM NAMES W/NUMBER
GRIDLINES
TYPE A UNIT SYMBOLS
PLACE FIRE WALL SYMBOL
A3.xx ROOF PLANS (1/8"=1'-0") | Assigned to | 50% DD
|  | ASSOCIATE | PM
ROOF PLAN MODELING
DESIGN AND MODELING:
ROOF SLOPES (COORDINATE STRUCTURAL FRAMING)
ROOF CRICKETS, ROOF DRAINS, SCUPPERS, ETC.
ROOF SEPARATION CURB
A/C EQUIPMENT AND SERVICE WALLS
SHOW TOP FLOOR WALLS IN HALF TONE
SHOW GRID LINE
SHEET DESIGN
GENERAL NOTES AND SYMBOLS (REVISE TEMPLATE FOR PROJECT)
MATCH LINES
ORB TITLE, GRAPHIC SCALE & NORTH ARROW
BUILDING KEY PLAN
A3.xx ROOF PLANS (1/8"=1'-0") | Assigned to | 50% DD
|  | ASSOCIATE | PM
ROOF PLAN ANNOTATIONS
REFERENCE MATCH LINE
A3.xx BUILDING ELEVATIONS | Assigned to | 50% DD
|  | ASSOCIATE | PM
SHEET DESIGN
BUILDING KEY PLAN
A5.xx ENLARGED PLANS (COMMON AREAS, LEASING, REC, FITNESS, ETC) (1/4"=1'-0") | Assigned to | 50% DD
|  | ASSOCIATE | PM
SHEET DESIGN
GENERAL NOTES AND SYMBOLS (REVISE TEMPLATE FOR PROJECT)
ORB TITLE & GRAPHIC SCALE
KEYNOTES
ENLARGED PLAN ANNOTATIONS
ROOM NAMES & NUMBER
GRIDLINES
APPLIANCE LABELS
A6.xx ENLARGED PLANS (STAIR, ELEVATOR, TRASH CHUTE, ETC.) (1/4"=1'-0") | Assigned to | 50% DD
|  | ASSOCIATE | PM
ENLARGED PLAN MODELING
VERIFY EXIT PASSAGE WAYS AT GROUND LEVEL AS REQUIRED
STAIR, GUARDRAILS, HANDRAILS, ETC
VERTICAL CLEARANCE BARRIER
STAIR GATE AT DISCHARGE LEVEL IF NEEDED (2018 IBC 1023.8)

## 100% DD
100% DD Checklist
GENERAL | Assigned to | 100% DD
|  | ASSOCIATE | PM
GENERAL/PROJECT MANAGEMENT
ADDRESSING PLAN
SUBMITT
A1.xx LIFE SAFETY COVER | Assigned to | 100% DD
|  | ASSOCIATE | PM
LIFE SAFETY KEY PLAN
KEY PLAN
BLDG NUMBER
SECTION TAG
FIRE WALL LABELS
ORB TITLE & NORTH ARROW
LIFE SAFETY KEY SECTION
SECTION
COLOR CODE OF FIRE ASSEMBLIES (WALLS, FLOOR-CEILING AND ROOF- CEILING)
BLDG NUMBER AND OCCUPANCY TYPE
BUILDING LEVELS AND GRADE LEVEL
CONSTRUCTION TYPE
EXIT DISCHARGE LEVEL
CALLOUT OCCUPANCY SEPARATION (SEPARATED USE, NON-SEPARATED USE, ACCESSORY USE, ETC)
FIRE WALL LABELS
FLAME SPREAD AND FINISHES FIRE CLASSIFICATION (IBC 803.11)
ACCESIBILITY COMPLIANCE
OCCUPANT LOAD ANALYSIS PER BUILDING
OCCUPANT LOAD ANALYSIS PER COURTYARD AREA
BUILDING AREA ANALYSIS
BUILDING CODES LIST
FIRE RESISTANCE RATING TABLE PER 2018 IBC TABLE 601 AND 602
GENERAL NOTES AND SYMBOLS (REVISE TEMPLATE FOR PROJECT)
FIRE/SMOKE INT/EXT WALL & FLOOR/ROOF ASSEMBLIES LEGEND
A1.5x LIFE SAFETY PLANS - OVERALL BLDG PLANS | Assigned to | 100% DD
|  | ASSOCIATE | PM
LIFE SAFETY PLAN MODELING
LOCATE FDC (STAND PIPE) NEXT TO FIRE WALL AS NEEDED
MODEL FIRE WALLS, CORRIDOR DOORS, AND MISC. ITEMS AS REQUIRED
IMAGINARY PROPERTY LINE
SHEET DESIGN
SYMBOLS (REVISE TEMPLATE FOR PROJECT)
FIRE/SMOKE INT/EXT WALL & FLOOR/ROOF ASSEMBLIES LEGEND
BUILDING KEY PLAN
ORB TITLE, GRAPHIC SCALE & NORTH ARROW
LIFE SAFETY SECTIONS
OPEN PARKING GARAGE CALCULATION (2018 IBC 406.5.2) WHERE OCCURS
LIFE SAFETY PLAN ANNOTATIONS
EXIT TRAVEL DISTANCE (IBC 1016.1)
COMMON PATH OF EGRESS TRAVEL (IBC TABLE 1006.2.1)
EXIT TRAVEL DEAD-END (50'-0" MAX.) (IBC SECTION 903.3.1.1 PER IBC 1020.4 EXP .2)
STANDPIPE TRAVEL DISTANCE (905.4.6)
LENGTH OF TRAVEL DISTANCE LABELS
A1.5x LIFE SAFETY PLANS - OVERALL BLDG PLANS | Assigned to | 100% DD
|  | ASSOCIATE | PM
KEYNOTES
CREATE KEYNOTES LIST
A1.5x LIFE SAFETY PLANS - ENLARGED BLDG PLANS | Assigned to | 100% DD
|  | ASSOCIATE | PM
LIFE SAFETY PLAN MODELING
COLOR FILL ON LIFE SAFETY PLAN FOR OCCUPANCY CLASSIFICATION
COLOR FILL ON LIFE SAFETY PLAN FOR FIRE/SMOKE WALL ASSEMBLIES
SHEET DESIGN
SYMBOLS (REVISE TEMPLATE FOR PROJECT)
FIRE/SMOKE INT/EXT WALL & FLOOR/ROOF ASSEMBLIES LEGEND
BUILDING KEY PLAN
SPLIT BLDG VIEWS AND ADD MATCH LINES
ORB TITLE, GRAPHIC SCALE & NORTH ARROW
LIFE SAFETY SECTIONS
OPEN PARKING GARAGE CALCULATION (2018 IBC 406.5.2) WHERE OCCURS
A1.5x LIFE SAFETY PLANS - ENLARGED BLDG PLANS | Assigned to | 100% DD
|  | ASSOCIATE | PM
LIFE SAFETY PLAN ANNOTATIONS
PANIC HARDWARE SYMBOL AT DOORS
AREA LABEL (AREA NAME, OCCUPANCY GROUP, AREA S.F. AND OCCUPANT LOAD)
ACCESSIBLE UNIT LABEL
KEYNOTES
CREATE KEYNOTES LIST
A2.xx UNIT PLANS (1/4"=1'-0") | Assigned to | 100% DD
|  | ASSOCIATE | PM
SHEET DESIGN
GENERAL NOTES AND SYMBOLS (REVISE TEMPLATE FOR PROJECT)
PLACE INTERIOR ELEVATIONS ON SHEET
PLACE KEYNOTE SCHEDULE
UNIT PLAN ANNOTATIONS
ROOM NAMES (ONLY)
A2.xx UNIT PLANS (1/4"=1'-0") | Assigned to | 100% DD
|  | ASSOCIATE | PM
DIMENSIONS
OVERALL DIMENSIONS
KEYNOTES
UPDATE KEYNOTES LIST
ANSI UNIT PLANS
CLEAR FLOOR SPACES
ACCESIBLE ROUTE
TURNING SPACE IN ALL ROOMS IN ANSI TYPE 'A' UNITS
CRITICAL DIMENSIONS & NOTES
DOOR SCHEDULE
CREATE DOOR SCHEDULE
DOOR TYPES SCHEDULE ELEVATION FROM TEMPLATE
DOOR HARDWARE
WINDOW SCHEDULE
CREATE WINDOW SCHEDULE
WINDOW TYPES FROM TEMPLATE
A3.xx BUILDING PLANS | Assigned to | 100% DD
|  | ASSOCIATE | PM
BUILDING PLAN MODELING
DESIGN AND MODELING
GARAGE VENTILATION SHAFT AS NEEDED
ANCILLARY SPACES (CORRIDOR STORAGE, A/C, ELEVATOR LOBBY, ETC)
MAIL BOXES AND PARCEL LOCKERS/STORAGE
VERTICAL CIRCULATIONS (STAIRS AND ELEVATORS)
COMMON AREAS (LEASING, REC, FITNESS, ETC)
COORDINATE COLUMNS AND SHEARWALLS WITH STRUCTURAL
SHEET DESIGN
GENERAL NOTES AND SYMBOLS (REVISE TEMPLATE FOR PROJECT)
PLACE KEYNOTE SCHEDULE
UPDATE GENERAL NOTES AND SYMBOLS
A3.xx BUILDING PLANS | Assigned to | 100% DD
|  | ASSOCIATE | PM
BUILDING PLAN ANNOTATIONS
ENLARGED PLAN CALLOUTS
REVIEW ENLARGED BUILDING ELEVATION TAGS
TRASH CHUTE CARTS AND MISCELLANEOUS ITEMS
REVIEW BUILDING SECTION TAGS (LOOKING PLAN NORTH AND EAST)
DIMENSIONS
GRIDLINES DIMENSIONS
KEYNOTES
CREATE KEYNOTES LIST
A3.xx ROOF PLANS (1/8"=1'-0") | Assigned to | 100% DD
|  | ASSOCIATE | PM
ROOF PLAN MODELING
DESIGN AND MODELING:
FIRE WALLS AT ROOF
STAIR AND ELEVATOR TOWERS
A3.xx ROOF PLANS (1/8"=1'-0") | Assigned to | 100% DD
|  | ASSOCIATE | PM
ROOF PLAN ANNOTATIONS
SLOPE ARROWS
FIRE WALL SYMBOL
FIRE WALL AREA OF NO PENETRATION HATCH
UNIT NAMES AND NUMBER
DIMENSIONS
FIRE WALL NO OPENINGS AREA DIMENSION
KEYNOTES
CREATE KEYNOTES LIST
A3.xx BUILDING ELEVATIONS | Assigned to | 100% DD
|  | ASSOCIATE | PM
BUILDING ELEVATIONS MODELING
SHOW:
SCUPPERS AT BALCONIES
CREATE ENLARGED ELEVATION VIEWS
BUILDING MOUNTED UTILITIES (S.E.S., METERS, ETC)
SHEET DESIGN
GENERAL NOTES (REVISE TEMPLATE FOR PROJECT)
BUILDING ELEMENTS
DASH IN A/C UNITS ON ROOF
BUILDING MOUNTED SIGNS
BUILDING ELEVATION ANNOTATIONS
GRID LINES
KEYNOTES
CREATE KEYNOTES LIST
A4.xx BUILDING SECTIONS (1/16"=1'-0") | Assigned to | 100% DD
|  | ASSOCIATE | PM
SHEET DESIGN
BUILDING KEY PLAN
LAYOUT BLDG SECTIONS ON SHEET
ORB TITLE & GRAPHIC SCALE
BUILDING SECTION ANNOTATIONS
GRIDLINES
A4.xx WALL SECTIONS (3/8"=1'-0") | Assigned to | 100% DD
|  | ASSOCIATE | PM
SHEET DESIGN
BUILDING KEY PLAN
LAYOUT WALL SECTIONS ON SHEET
ORB TITLE & GRAPHIC SCALE
KEYNOTES
CREATE KEYNOTES LIST
A5.xx ENLARGED PLANS (COMMON AREAS, LEASING, REC, FITNESS, ETC) (1/4"=1'-0") | Assigned to | 100% DD
|  | ASSOCIATE | PM
COMMON AREAS MODELING
REVIEW WINDOWS, DOORS & STOREFRONTS
RESTROOM ACCESSORIES (TOILET PAPER HOLDERS/TOWEL BARS/ETC.)
KITCHEN, COUNTERTOPS, ETC. (COORDINATE WITH I.D.)
MAIL BOXES, PARCEL, ETC
SHEET DESIGN
PLACE INTERIOR ELEVATIONS ON SHEET (MAY BE A SEPARATE SHEET)
ENLARGED PLAN ANNOTATIONS
CLEAR FLOOR SPACES (INCLUDING DOORS)
A5.xx ENLARGED PLANS (COMMON AREAS, LEASING, REC, FITNESS, ETC) (1/4"=1'-0") | Assigned to | 100% DD
|  | ASSOCIATE | PM
KEYNOTES
CREATE KEYNOTES LIST
A6.xx ENLARGED PLANS (STAIR, ELEVATOR, TRASH CHUTE, ETC.) (1/4"=1'-0") | Assigned to | 100% DD
|  | ASSOCIATE | PM
ENLARGED PLAN MODELING
FURRING WALL
STANDPIPE & STANDPIPE PROTECTION AT STAIR TOWERS
STANDPIPE CABINET AT HORIZONTAL EXITS
ROOF ACCESS (HATCH, LADDER)
ELEVATOR CAB
TRASH CHUTE SYSTEM & CHUTE DOOR
CORRIDOR STORAGE, ELEVATOR LOBBY, ETC (ACCESSIBLE STORAGE)
EMERGENCY RESPONDER RADIO COVERAGE SYSTEM (ERRC, 2018 IBC 918)
ELEVATOR TOWER ROOF
SHEET DESIGN
GENERAL NOTES AND SYMBOLS (REVISE TEMPLATE FOR PROJECT)
UPDATE GENERAL NOTES AND SYMBOLS
ORB TITLE & GRAPHIC SCALE
KEYNOTES
A6.xx ENLARGED PLANS (STAIR, ELEVATOR, TRASH CHUTE, ETC.) (1/4"=1'-0") | Assigned to | 100% DD
|  | ASSOCIATE | PM
ENLARGED PLAN ANNOTATIONS
ROOM NAMES & NUMBER
CLEAR FLOOR SPACES
TURNING RADIUS
KEYNOTES
CREATE KEYNOTES LIST
A6.xx STAIR/ELEV SECTIONS (1/4"=1'-0") | Assigned to | 100% DD
|  | ASSOCIATE | PM
KEYNOTES
CREATE KEYNOTES LIST

## 50% CD
50% CD Checklist
GENERAL |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
GENERAL/PROJECT MANAGEMENT
ADDRESSING PLAN
APPROVAL
A1.xx LIFE SAFETY COVER |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
LIFE SAFETY KEY SECTION
EXTERIOR OPENINGS CALCULATION TABLE (2018 IBC 705.8)
BUILDING KEY PLAN WITH ELEVATION TAGS
CODE ANALYSIS
A1.5x LIFE SAFETY PLANS - OVERALL BLDG PLANS |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
KEYNOTES
UPDATE KEYNOTES LIST
PLACE KEYNOTES ON BUILDING PLANS
A1.5x LIFE SAFETY PLANS - ENLARGED BLDG PLANS |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
LIFE SAFETY PLAN ANNOTATIONS
MEANS OF EGRESS LABEL FOR DOORS (DOOR, EXIT WIDTH PROVIDED, MAX. OCCUPANT LOAD CAPACITY (2018 IBC 1005.3.2 EXP. 1), ACTUAL OCCUPANT LOAD, OPENING PROTECTION RATING (2018 IBC TABLE 716.1(2))
MEANS OF EGRESS LABEL FOR STAIRS (STAIR, EXIT WIDTH PROVIDED, MAX. OCCUPANT LOAD CAPACITY (2018 IBC 1005.3.1 EXP.1), ACTUAL OCCUPANT LOAD)
KEYNOTES
UPDATE KEYNOTES LIST
PLACE KEYNOTES ON BUILDING PLANS
A2.xx UNIT PLANS (1/4"=1'-0") |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
SHEET DESIGN
PLACE DOOR SCHEDULE ON SHEET
PLACE WINDOW SCHEDULE ON SHEET
UPDATE GENERAL NOTES AND SYMBOLS
UNIT PLAN ANNOTATIONS
INTERIOR ELEVATION TAGS
VERIFY VANITY, SHOWER & TUB SIZE NOTES
A2.xx UNIT PLANS (1/4"=1'-0") |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
DIMENSIONS
PERIMETER DIMENSIONS
KEYNOTES
UPDATE KEYNOTES LIST
ADD DETAIL REFERENCE TO KEYNOTES
UPDATE DETAIL REFERENCE TO KEYNOTES
A3.xx BUILDING PLANS |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
BUILDING PLAN MODELING
DESIGN AND MODELING:
COORDINATE COLUMNS AND SHEARWALLS WITH STRUCTURAL
SHEET DESIGN
UPDATE GENERAL NOTES AND SYMBOLS
A3.xx BUILDING PLANS |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
BUILDING PLAN ANNOTATIONS
COMMONS/CORRIDORS DOOR TAGS
COMMONS/CORRIDORS WINDOW TAGS
COMMONS/CORRIDORS STOREFRONT TAGS
DIMENSIONS
DRIVEWAY & PARKING SPACES DIMENSIONS
KEYNOTES
UPDATE KEYNOTES LIST
PLACE KEYNOTES ON BUILDING PLANS
A3.xx REFLECTED CEILING PLANS (1/8"=1'-0") |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
REFLECTED CEILING PLAN MODELING
SHOW WALLS, DOORS & WINDOWS (HALFTONE)
TURN OFF EVERYTHING ELSE IN THE UNIT
SHOW ROOF HATCH & ATTICC ACCESS
DROPPED CEILING AT CORRIDORS AND ANCILLARY SPACES
COORDINATE COORRIDOR CROSSINGS WITH PLUMBING (TEAL SYSTEM)
SHEET DESIGN
BUILDING KEY PLAN
MATCH LINE
ORB TITLE, GRAPHIC SCALE & NORTH ARROW
PLACE KEYNOTE SCHEDULE
A3.xx ROOF PLANS (1/8"=1'-0") |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
ROOF PLAN MODELING
ROOF VENTS AS NEEDED
ROOF ACCESS HATCH
CORRIDOR AIR CONDITIONING UNIT FRESH AIR SHAFT AT ROOF
TRASH CHUTE EXHAUST FAN
ELEVATOR SHAFT AIR CONDITIONING UNIT
STANDPIPE AT ROOF
A3.xx BUILDING ELEVATIONS |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
BUILDING ELEMENTS
STUCCO JOINTS
STUCCO EXPANSION JOINTS
BUILDING EXPANSION JOINT (AS REQUIRED)
BUILDING ELEVATION ANNOTATIONS
FIRE WALL AREA OF NO PENETRATION HATCH
UNIT NAME REFERENCE LABEL
A4.xx BUILDING SECTIONS (1/16"=1'-0") |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
MODELING
FOUNDATION (COORDINATE WITH STRUCTURAL)
A4.xx WALL SECTIONS (3/8"=1'-0") |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
WALL SECTION MODELING
FOUNDATION (COORDINATE WITH STRUCTURAL)
COORDINATE AND SHOW STRUCTURAL ELEMENTS (BEAMS, FRAMING, ETC)
COORDINATE AND SHOW DROPPED CEILINGS
WALL SECTION ANNOTATIONS
ROOM NAMES W/NUMBER
GRIDLINES
ANNOTATE BLDG COMPONENTS (FRAMING, INSULATION, FINISHES, ETC)
A5.00 SCHEDULES |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
CREATE SCHEDULES AND VIEWS
COMMONS DOOR SCHEDULE
COMMONS DOOR TYPE ELEVATIONS (FROM TEMPLATE)
COMMONS DOOR HARDWARE SCHEDULE (FROM TEMPLATE)
COMMONS WINDOW SCHEDULE
COMMONS WINDOW TYPE ELEVATIONS
STOREFRONT ELEVATIONS
SHEET DESIGN
SCHEDULES (DOORS, WINDOWS, GATES)
DOORS AND WINDOWS GENERAL NOTES (REVISE TEMPLATE FOR PROJECT)
DOOR ABBREVIATIONS
PLACE DOOR TYPES ELEVATIONS
PLACE WINDOW TYPES ELEVATIONS
PLACE STOREFRONT TYPES ELEVATIONS
PLACE HARDWARE SCHEDULE
GATE CLEARANCE DETAIL
A5.00 SCHEDULES |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
ANNOTATIONS AND COORDINATION
COORDINATE DOOR NUMBERS WITH ROOM NUMBERS
A5.xx ENLARGED PLANS (COMMON AREAS, LEASING, REC, FITNESS, ETC) (1/4"=1'-0") |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
COMMON AREAS MODELING
DROPPED CEILINGS (COORDINATE W/ MECHANICAL & INTERIOR DESIGN)
RESTROOM (REVIEW AND COORDINATE WITH I.D.)
INTERIOR ELEVATIONS
COORDINATE SPECIALTY ITEMS WITH I.D.
COORDINATE STRUCTURAL COMPONENTS
ENLARGED PLAN ANNOTATIONS
DOOR TAGS
WINDOW TAGS
STOREFRONT TAGS
INTERIOR ELEVATION TAGS
ENLARGED PLANS CALLOUTS
A5.xx ENLARGED PLANS (COMMON AREAS, LEASING, REC, FITNESS, ETC) (1/4"=1'-0") |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
INTERIOR ELEVATIONS
CREATE VIEWS AND PLACE ON SHEET
A6.xx ENLARGED PLANS (STAIR, ELEVATOR, TRASH CHUTE, ETC.) (1/4"=1'-0") |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
ENLARGED PLAN MODELING
DROPPED CEILING (COORDINATE WITH MECHANICAL)
CORRIDOR A/C UNITS AND FRESH AIR SHAFT
ELECTRICAL METERS, IDF, MDF
ELEVATOR DISCONNECT CLOSET (NORMALLY AT TOP LEVEL)
ELEVATOR A/C AT ROOF
ELEVATOR RECESSED PUMP PIT
ELEVATOR PIT LADDER
A6.xx STAIR/ELEV SECTIONS (1/4"=1'-0") |  | Assigned to | 50% CD
|  |  | ASSOCIATE | PM
STAIR/ELEV SECTION MODELING
FOUNDATION (COORDINATE WITH STRUCTURAL)
COORDINATE AND SHOW STRUCTURAL ELEMENTS (BEAMS, FRAMING, ETC)
COORDINATE AND SHOW DROPPED CEILINGS
CHUTE EXHAUST VENT
SHEET DESIGN
GENERAL NOTES AND SYMBOLS (SAME AS ENLARGED PLANS)
LAYOUT WALL SECTIONS ON SHEET
ORB TITLE & GRAPHIC SCALE
STAIR/ELEV SECTION ANNOTATIONS
ROOM NAMES W/NUMBER
GRIDLINES

## 75% CD
75% CD Checklist
A1.xx LIFE SAFETY COVER | Assigned to | 75% CD
|  | ASSOCIATE | PM
LIFE SAFETY KEY SECTION
COORDINATE DETAIL REFERENCES
THERMAL ENVELOPE VALUES
A1.5x LIFE SAFETY PLANS - OVERALL BLDG PLANS | Assigned to | 75% CD
|  | ASSOCIATE | PM
LIFE SAFETY PLAN MODELING
PLACE CORRIDOR FIRE EXTINGUISHER (IBC TABLE 906.3(1))
EXIT SIGN LOCATIONS (COORDINATE WITH ELECTRICAL)
SHEET DESIGN
UPDATE FIRE/SMOKE INT/EXT WALL & FLOOR/ROOF ASSEMBLIES LEGEND
UPDATE OPEN PARKING GARAGE CALCULATION (2018 IBC 406.5.2) WHERE OCCURS
LIFE SAFETY PLAN ANNOTATIONS
TRAVEL DISTANCE TO FIRE EXTINGUISHER (IBC TABLE 906.3(1))
LENGTH OF FIRE EXTINGUISHER TRAVEL DISTANCE LABELS
LOCATE EXIT SIGN SYMBOLS
DIMENSIONS
DISTANCE BETWEEN IMAGINARY PROPERTY LINE AND BUILDING EXTERIOR WALLS
FIRE WALL AREA OF NO PENETRATION DIMENSION
A1.5x LIFE SAFETY PLANS - OVERALL BLDG PLANS | Assigned to | 75% CD
|  | ASSOCIATE | PM
KEYNOTES
UPDATE KEYNOTES LIST
PLACE KEYNOTES ON BUILDING PLANS
ADD DETAIL REFERENCE TO KEYNOTES
A1.5x LIFE SAFETY PLANS - ENLARGED BLDG PLANS | Assigned to | 75% CD
|  | ASSOCIATE | PM
SHEET DESIGN
UPDATE FIRE/SMOKE INT/EXT WALL & FLOOR/ROOF ASSEMBLIES LEGEND
UPDATE OPEN PARKING GARAGE CALCULATION (2018 IBC 406.5.2) WHERE OCCURS
A1.5x LIFE SAFETY PLANS - ENLARGED BLDG PLANS | Assigned to | 75% CD
|  | ASSOCIATE | PM
LIFE SAFETY PLAN ANNOTATIONS
WALL TYPE TAGS
DETAIL CALLOUTS
HORIZONTAL EXIT REFUGE AREA HATCH AND CALCULATIONS NOTE WITH CODE REFERENCE (2018 IBC 1026.4)
ADD NOTE CALLOUT TO ALL STANDPIPES
HORIZONTAL EXIT INFORMATION
EXIT PASSAGEWAY HATCH (2-HR FIRE BARRIER WALLS & 2-HR HORZ. ASSEMBLY)
ADD OCCUPANT LOAD CALCULATION NEXT TO STAIR TAGS
DIMENSIONS
DIAGONAL DISTANCE AND DOOR TO DOOR DISTANCE (WHEN MORE THAN ONE DOOR REQUIRED FROM ONE SPACE)
FIRE WALL AREA OF NO PENETRATION DIMENSION
EXIT TRAVEL DEAD-END TAGS
KEYNOTES
UPDATE KEYNOTES LIST
PLACE KEYNOTES ON BUILDING PLANS
ADD DETAIL REFERENCE TO KEYNOTES
A2.xx UNIT PLANS (1/4"=1'-0") | Assigned to | 75% CD
|  | ASSOCIATE | PM
UNIT PLAN MODELING
DROP CEILINGS (COORDINATE W/ MECHANICAL)
SHEET DESIGN
UPDATE GENERAL NOTES AND SYMBOLS
UNIT PLAN ANNOTATIONS
DOOR TAGS
WINDOW TAGS
WALL TYPE TAGS
A2.xx UNIT PLANS (1/4"=1'-0") | Assigned to | 75% CD
|  | ASSOCIATE | PM
DIMENSIONS
INTERIOR DIMENSIONS (100% FINAL)
KEYNOTES
UPDATE KEYNOTES LIST
UPDATE DETAIL REFERENCE TO KEYNOTES
PLACE KEYNOTES ON UNIT PLAN
PLACE KEYNOTES ON ANSI PLAN
ANSI UNIT PLANS
PLACE GENERAL KEYNOTES
PLACE ANSI TYPE 'A' KEYNOTES AT ANSI TYPE 'A' UNITS ONLY
INTERIOR ELEVATIONS
DIMENSIONS & NOTES
PLACE GENERAL KEYNOTES
PLACE ANSI TYPE 'A' KEYNOTES AT ANSI TYPE 'A' UNITS ONLY
A3.xx BUILDING PLANS | Assigned to | 75% CD
|  | ASSOCIATE | PM
BUILDING PLAN MODELING
DESIGN AND MODELING:
COORDINATE COLUMNS AND SHEARWALLS WITH STRUCTURAL
SHEET DESIGN
UPDATE GENERAL NOTES AND SYMBOLS
INSULATION SCHEDULE
A3.xx BUILDING PLANS | Assigned to | 75% CD
|  | ASSOCIATE | PM
BUILDING PLAN ANNOTATIONS
REVIEW BUILDING SECTION TAGS (LOOKING PLAN NORTH AND EAST)
REVIEW WALL SECTION TAGS (LOOKING PLAN NORTH AND EAST)
WALL TYPE TAGS
DETAIL CALLOUTS
DIMENSIONS
PERIMETER DIMENSIONS (OVERALL PLAN)
FULLY DIMENSION ENLARGED BUILDING PLANS
KEYNOTES
UPDATE KEYNOTES LIST
PLACE KEYNOTES ON BUILDING PLANS
ADD DETAIL REFERENCE TO KEYNOTES
A3.xx REFLECTED CEILING PLANS (1/8"=1'-0") | Assigned to | 75% CD
|  | ASSOCIATE | PM
REFLECTED CEILING PLAN MODELING
DRAW LIGHTS (COORDINATE W/ELECTRICAL)
DRAW EXIT SIGNS (COORDINATE W/ELECTRICAL)
REFLECTED CEILING PLAN ANNOTATIONS
CEILING HEIGHT TAG
UNIT AND COMMON AREAS NAMES AND NUMBER
REFERENCE SHEET FOR COMMON AREAS RCP
CEILING DIMENSIONS
KEYNOTES
CREATE KEYNOTES LIST
PLACE KEYNOTES
ADD DETAIL REFERENCE TO KEYNOTES
A3.xx ROOF PLANS (1/8"=1'-0") | Assigned to | 75% CD
|  | ASSOCIATE | PM
SHEET DESIGN
UPDATE GENERAL NOTES AND SYMBOLS
A3.xx ROOF PLANS (1/8"=1'-0") | Assigned to | 75% CD
|  | ASSOCIATE | PM
ROOF PLAN ANNOTATIONS
PARAPETS SPOT ELEVATION
DETAIL CALLOUTS
ENLARGED PLANS CALLOUTS
REVIEW SECTION TAGS
KEYNOTES
UPDATE KEYNOTES LIST
PLACE KEYNOTES ON ROOF PLANS
ADD DETAIL REFERENCE TO KEYNOTES
A3.xx BUILDING ELEVATIONS | Assigned to | 75% CD
|  | ASSOCIATE | PM
BUILDING ELEMENTS
BUILDING MOUNTED SIGNS
THROUGH WALL VENTS
BUILDING EXTERIOR LIGHTS
BUILDING ELEVATION ANNOTATIONS
DETAIL CALLOUTS
REVIEW/UPDATE MATERIAL TAGS
REVIEW SECTION TAGS
A3.xx BUILDING ELEVATIONS | Assigned to | 75% CD
|  | ASSOCIATE | PM
KEYNOTES
REVIEW/UPDATE KEYNOTES LIST
PLACE KEYNOTES
ADD DETAIL REFERENCE TO KEYNOTES
A4.xx BUILDING SECTIONS (1/16"=1'-0") | Assigned to | 75% CD
|  | ASSOCIATE | PM
BUILDING SECTION ANNOTATIONS
ROOM NAMES W/NUMBER
WALL SECTIONS CALLOUTS
DETAIL CALLOUTS
A4.xx WALL SECTIONS (3/8"=1'-0") | Assigned to | 75% CD
|  | ASSOCIATE | PM
WALL SECTION ANNOTATIONS
DETAIL CALLOUTS
KEYNOTES
WALL TYPE TAGS
FLOOR-CEILING TAGS
ROOF-CEILING TAGS
BALCONY/ROOF SLOPE ARROWS
DIMENSIONS
DIMENSIONS TO TOP/BOTTOM POPOUTS
DIMENSIONS TO LOW WALLS/GUARDRAILS
DIMENSIONS TO CANOPIES
DIMENSIONS TO ARCHITECTURAL FEATURES
KEYNOTES
PLACE KEYNOTES ON SECTIONS
ADD DETAIL REFERENCE TO KEYNOTES
UPDATE KEYNOTES LIST
A5.00 SCHEDULES | Assigned to | 75% CD
|  | ASSOCIATE | PM
CREATE SCHEDULES AND VIEWS
GATE SCHEDULE
GATE ELEVATIONS
SHEET DESIGN
UPDATE DOORS AND WINDOWS GENERAL NOTES
A5.00 SCHEDULES | Assigned to | 75% CD
|  | ASSOCIATE | PM
ANNOTATIONS AND COORDINATION
REVIEW DOORS ARE MODELED CORRECTLY
COORDINATE HARDWARE SET ON EACH DOOR
VERIFY DOOR LOCATION (ROOM)
VERIFY DOOR FIRE RATING
COORDINATE WINDOW TYPES WITH SCHEDULE
VERIFY ALL COMMONS WINDOWS ARE IN SCHEDULE
VERIFY WINDOWS TEMPERED GLASS LOCATIONS
DIMENSION EACH STOREFRONT ELEVATION
ADD STOREFRONT DETAIL CALLOUTS
ADD TEMPERED NOTATION TO EACH STOREFRONT GLASS PANEL AS REQUIRED
COORDINATE GATE SCHEDULE WITH PROJECT
A5.xx ENLARGED PLANS (COMMON AREAS, LEASING, REC, FITNESS, ETC) (1/4"=1'-0") | Assigned to | 75% CD
|  | ASSOCIATE | PM
SHEET DESIGN
UPDATE GENERAL NOTES AND SYMBOLS
ENLARGED PLAN ANNOTATIONS
WALL TYPE TAGS
DETAIL CALLOUTS
REVIEW WALL SECTION TAGS
A5.xx ENLARGED PLANS (COMMON AREAS, LEASING, REC, FITNESS, ETC) (1/4"=1'-0") | Assigned to | 75% CD
|  | ASSOCIATE | PM
DIMENSIONS
DIMENSION ALL WALLS, WINDOWS, STOREFRONT, COLUMNS AND MISCELLANEOUS COMPONENTS
KEYNOTES
PLACE KEYNOTES ON ENLARGED PLANS
ADD DETAIL REFERENCE TO KEYNOTES
UPDATE KEYNOTES LIST
INTERIOR ELEVATIONS
APPLIANCE LABELS
DIMENSIONS
DETAIL CALLOUTS
PLACE KEYNOTES
A6.xx ENLARGED PLANS (STAIR, ELEVATOR, TRASH CHUTE, ETC.) (1/4"=1'-0") | Assigned to | 75% CD
|  | ASSOCIATE | PM
ENLARGED PLAN ANNOTATIONS
DOOR TAGS
WINDOW TAGS
WALL TYPE TAGS
DETAIL CALLOUTS
STAIRS AND/OR RAMPS DN & UP ARROW
REVIEW STAIR & ELEVATOR SECTION CALLOUTS
DIMENSIONS
DIMENSION ALL WALLS, COLUMNS AND MISCELLANEOUS BLDG COMPONENTS
STAIR INFORMATION (TREADS, RISERS, LANDING)
ELEVATOR HOISTWAY DIMENSIONS
CHUTE CENTERLINE
DOOR OPENINGS AT CMU AND CONC. WALLS
SUMP CENTERLINE AND SIZE
KEYNOTES
PLACE KEYNOTES ON ENLARGED PLANS
ADD DETAIL REFERENCE TO KEYNOTES
UPDATE KEYNOTES LIST
A6.xx STAIR/ELEV SECTIONS (1/4"=1'-0") | Assigned to | 75% CD
|  | ASSOCIATE | PM
STAIR/ELEV SECTION ANNOTATIONS
DETAIL CALLOUTS
KEYNOTES
WALL TYPE TAGS
FLOOR-CEILING TAGS
ROOF-CEILING TAGS
ANNOTATE BLDG COMPONENTS (FRAMING, INSULATION, FINISHES, ETC)
ELEVATOR ROOF SLOPE ARROW
DIMENSIONS
DIMENSION STAIR RISER
DIMENSION WINDOWS AND/OR OPENINGS IF APPLICABLE
ELEVATOR PIT/SUMP DEPTH
ELEVATOR ROOF ELEVATIONS
ELEVATOR OVERHEAD BEAM AND MIN. CEILING HEIGHT
CLEARANCE TO CHUTE DISCHARGE OPENING
A6.xx STAIR/ELEV SECTIONS (1/4"=1'-0") | Assigned to | 75% CD
|  | ASSOCIATE | PM
KEYNOTES
PLACE KEYNOTES ON SECTIONS
ADD DETAIL REFERENCE TO KEYNOTES
UPDATE KEYNOTES LIST

## 100% CD
100% CD Checklist
A1.xx LIFE SAFETY COVER |  | Assigned to | 100% CD
|  |  | ASSOCIATE | PM
LIFE SAFETY KEY SECTION
CODE ANALYSIS
UPDATE GENERAL NOTES AND SYMBOLS
A1.5x LIFE SAFETY PLANS - OVERALL BLDG PLANS |  | Assigned to | 100% CD
|  |  | ASSOCIATE | PM
KEYNOTES
UPDATE KEYNOTES LIST
PLACE KEYNOTES ON BUILDING PLANS
UPDATE DETAIL REFERENCE TO KEYNOTES
A1.5x LIFE SAFETY PLANS - ENLARGED BLDG PLANS |  | Assigned to | 100% CD
|  |  | ASSOCIATE | PM
KEYNOTES
UPDATE KEYNOTES LIST
PLACE KEYNOTES ON BUILDING PLANS
UPDATE DETAIL REFERENCE TO KEYNOTES
A2.xx UNIT PLANS (1/4"=1'-0") |  | Assigned to | 100% CD
|  |  | ASSOCIATE | PM
SHEET DESIGN
UPDATE GENERAL NOTES AND SYMBOLS
A2.xx UNIT PLANS (1/4"=1'-0") |  | Assigned to | 100% CD
|  |  | ASSOCIATE | PM
DIMENSIONS
INTERIOR DIMENSIONS (100% FINAL)
KEYNOTES
UPDATE KEYNOTES LIST
UPDATE DETAIL REFERENCE TO KEYNOTES
A3.xx BUILDING PLANS |  | Assigned to | 100% CD
|  |  | ASSOCIATE | PM
SHEET DESIGN
UPDATE GENERAL NOTES AND SYMBOLS
A3.xx BUILDING PLANS |  | Assigned to | 100% CD
|  |  | ASSOCIATE | PM
BUILDING PLAN ANNOTATIONS
WALL TYPE TAGS
DETAIL CALLOUTS
KEYNOTES
UPDATE KEYNOTES LIST
PLACE KEYNOTES ON BUILDING PLANS
UPDATE DETAIL REFERENCE TO KEYNOTES
A3.xx REFLECTED CEILING PLANS (1/8"=1'-0") |  | Assigned to | 100% CD
|  |  | ASSOCIATE | PM
KEYNOTES
UPDATE KEYNOTES LIST
UPDATE DETAIL REFERENCE TO KEYNOTES
A3.xx ROOF PLANS (1/8"=1'-0") |  | Assigned to | 100% CD
|  |  | ASSOCIATE | PM
KEYNOTES
UPDATE DETAIL REFERENCE TO KEYNOTES
A3.xx BUILDING ELEVATIONS |  | Assigned to | 100% CD
|  |  | ASSOCIATE | PM
SHEET DESIGN
UPDATE GENERAL NOTES
A3.xx BUILDING ELEVATIONS |  | Assigned to | 100% CD
|  |  | ASSOCIATE | PM
KEYNOTES
REVIEW/UPDATE DETAIL REFERENCE TO KEYNOTES
A4.xx WALL SECTIONS (3/8"=1'-0") |  | Assigned to | 100% CD
|  |  | ASSOCIATE | PM
KEYNOTES
UPDATE KEYNOTES LIST
UPDATE DETAIL REFERENCE TO KEYNOTES
A5.xx ENLARGED PLANS (COMMON AREAS, LEASING, REC, FITNESS, ETC) (1/4"=1'-0") |  | Assigned to | 100% CD
|  |  | ASSOCIATE | PM
DIMENSIONS
CHECK AND REVIEW DIMENSIONS
KEYNOTES
UPDATE KEYNOTES LIST
UPDATE DETAIL REFERENCE TO KEYNOTES
A6.xx ENLARGED PLANS (STAIR, ELEVATOR, TRASH CHUTE, ETC.) (1/4"=1'-0") |  | Assigned to | 100% CD
|  |  | ASSOCIATE | PM
DIMENSIONS
CHECK AND REVIEW DIMENSIONS
KEYNOTES
UPDATE KEYNOTES LIST
UPDATE DETAIL REFERENCE TO KEYNOTES
A6.xx STAIR/ELEV SECTIONS (1/4"=1'-0") |  | Assigned to | 100% CD
|  |  | ASSOCIATE | PM
KEYNOTES
UPDATE KEYNOTES LIST
UPDATE DETAIL REFERENCE TO KEYNOTES